## Sheet1
Society for web publishing Project Cost Estimate
Prepared by: Mahmoud Mourad Youssef | Date: 5/1/2023
Note: Change the WBS items and other entries to meet your project needs. This data is from Figure 7-1 of Schwalbe's text
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Planning |  |  |  | 203760 | 15.63%
1.1 Define project scope and objectives | 960 | 50 | 48000
1.2 Develop project schedule and budget | 1920 | 40 | 76800
1.3 Identify stakeholders and conduct stakeholder analysis | 320 | 20 | 6400
1.4 Identify and mitigate risks | 230 | 30 | 6900
2. Implementation
2.1 Develop system requirements | 125 | 60 | 65660
2.2 Design user interface | 440 | 35 | 6260 | 12000 | 0.9205%
2.3 Build and test system | 225 | 25 | 5000
2.4 Deployment plan | 375 | 45 | 19400
3. Deployment
3.1 Traing Users | 3 | 4000 | 12000
3.2 Deploy system to production | 20 | 1000 | 20000 | 614000 | 47.1%
3.3 monitor and maintain system | 7 | 3000 | 21000
4. Testing (10% of total hardware and software costs) | 100 | 200 | 20000
5. Closeout |  |  | 594000
5.1 conduct project review |  |  | 62600 | 62600 | 4.802%
5.2 get user acceptance |  |  |  | 194000 | 14.88%
5.3 close out the project | 100 | 500 | 50000
Total project cost estimate | 1920 | 75 | 144000
|  |  | 217272 | 217272 | 16.67%
1303632

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898