## Sheet1
Risk Register for Web Publishing System
Prepared by: Mahmoud Mourad Youssef
No. | Rank | Risk | Description | Category | Potential Responses | Probability | Impact | Status
1 | high | Cybersecurity | The system is vulnerable to cyber attacks and data breaches, which could result in the loss of sensitive data and damage to the organization's reputation. | technical Risks | Develop and implement a security plan, Conduct regular security assessments | medium | high | issue
2 | high | Inadequate performance | he system does not meet the specified performance requirements, such as response time, scalability, or security. This could lead to a poor user experience, and could result in additional costs for the project. | technical Risks | Conduct performance testing | medium | high | resolved
3 | high | Cost overruns | The project costs more than the allocated budget due to unexpected expenses or changes in scope. | budget risk | Establish a detailed project budget, Continuously monitor project costs | high | high | resolved
4 | medium | Unforeseen contingencies | Unexpected events or conditions occur that require additional resources to mitigate or address, such as a natural disaster or a pandemic. | budget risk | Develop a contingency plan, Have a contingency fund | low | medium | updated
5 | low | Dependence on external factors | The project schedule is dependent on factors outside of the team's control, such as approval from external stakeholders, and these factors delay the project schedule. | schedule risk | Identify external dependencies, Identify alternative solutions | high | medium | resolved
6 | low | Dependence on a single key resource | The project relies heavily on a single key resource, such as a critical team member, and this person is unable to continue working on the project due to illness, personal issues or other reasons | resource risk | Identify critical resources, Develop a backup plan, Have a redundancy plan | low | low | resolved